## Project Plan and Gantt
QuanLyBanQuanAo
Nguyễn Đỗ Quốc Tuấn
2016-10-10
2016-08-27
2016-10-10
70%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Nguyễn Đỗ Quốc Tuấn+Ngô Thị Tường Vy | 2016-08-27 | 2016-08-31 | 5 | Completed
Agree on objectives | Nguyễn Đỗ Quốc Tuấn+Ngô Thị Tường Vy | 2016-09-01 | 2016-09-05 | 5 | Completed
Plan | Nguyễn Đỗ Quốc Tuấn+Ngô Thị Tường Vy | 2016-09-06 | 2016-09-12 | 7 | Completed
Detailed Reqs. | Nguyễn Đỗ Quốc Tuấn | 2016-09-13 | 2016-09-17 | 5 | Completed
Technical Reqs. | Ngô Thị Tường Vy | 2016-09-13 | 2016-09-17 | 5 | Completed
Database Development | Nguyễn Đỗ Quốc Tuấn | 2016-09-18 | 2016-09-24 | 7 | Completed
UI Client | Ngô Thị Tường Vy | 2016-09-18 | 2016-10-01 | 14 | Completed
Connect Database | Nguyễn Đỗ Quốc Tuấn | 2016-09-25 | 2016-10-08 | 14 | Completed
Insert/Update/Query | Ngô Thị Tường Vy | 2016-10-02 | 2016-10-08 | 7 | Completed
Function 1 Thêm | Nguyễn Đỗ Quốc Tuấn | 2016-10-09 | 2016-10-15 | 7 | Completed
Function 2 Xóa | Ngô Thị Tường Vy | 2016-10-09 | 2016-10-15 | 7 | Completed
Function 3 Cập nhật | Nguyễn Đỗ Quốc Tuấn | 2016-10-16 | 2016-10-22 | 7 | Completed
Fixing | Ngô Thị Tường Vy | 2016-10-16 | 2016-10-29 | 14 | Completed
Testing | Nguyễn Đỗ Quốc Tuấn | 2016-10-30 | 2016-11-05 | 7 | Completed
Launch |  | 2016-11-13 | 2016-11-13 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Lê Khánh | Team leader, Developer | 1. Make the plan of the project. 2. Assign task for your member. 3. Design GUI/database. 4. Code. 5. Write document | kanelorange@gmail.com
Trần Minh Trung | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test 4. Analysis & design the system. | minhtrungdhth10e@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team