## Project Plan and Gantt
Project Name | QuanLyBanQuanAo
Project Manager | Nguyễn Đỗ Quốc Tuấn
Project Deliverable | 2016-10-10
Scope Statement:
Start Date | 2016-08-27
End Date | 2016-10-10
Overall Progress | 10%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Nguyễn Đỗ Quốc Tuấn | 2016-08-27 | 2016-08-27 | 0 | Completed
Agree on objectives | Ngô Thị Tường Vy | 2016-08-27 | 2016-08-27 | 0 | Completed
Detailed Reqs. | Nguyễn Đỗ Quốc Tuấn | 2016-08-28 | 2016-08-31 | 3 | Completed
Techincal Reqs. | Ngô Thị Tường Vy | 2016-08-28 | 2016-08-31 | 3 | Not started
DB Development | Nguyễn Đỗ Quốc Tuấn | 2016-08-29 | 2016-09-02 | 4 | Not started
Connect DB | Nguyễn Đỗ Quốc Tuấn | 2016-09-02 | 2016-09-06 | 4 | Not started
Insert/Update/Query | Ngô Thị Tường Vy | 2016-09-06 | 2016-09-11 | 5 | Not started
API Development | Ngô Thị Tường Vy | 2016-09-06 | 2016-09-11 | 5 | Not started
Function 1 | Nguyễn Đỗ Quốc Tuấn | 2016-09-06 | 2016-09-10 | 4 | Not started
Function 2… | Ngô Thị Tường Vy | 2016-09-11 | 2016-09-15 | 4 | Not started
UI Client | Ngô Thị Tường Vy | 2016-09-15 | 2016-09-20 | 5 | Not started
Testing | Nguyễn Đỗ Quốc Tuấn | 2016-09-20 | 2016-09-25 | 5 | Not started
Dev. Complete | Nguyễn Đỗ Quốc Tuấn | 2016-09-25 | 2016-09-29 | 4 | Not started
Hardware Config. | Ngô Thị Tường Vy | 2016-09-29 | 2016-10-04 | 5 | Not started
System Testing | Nguyễn Đỗ Quốc Tuấn | 2016-10-04 | 2016-10-09 | 5 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Lê Khánh | Team leader, Developer | 1. Make the plan of the project. 2. Assign task for your member. 3. Design GUI/database. 4. Code. 5. Write document | kanelorange@gmail.com
Trần Minh Trung | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test 4. Analysis & design the system. | minhtrungdhth10e@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team