## Project Plan and Gantt
|  | Project Name | QuanLyBanQuanAo
|  | Project Manager | Nguyễn Đỗ Quốc Tuấn
|  | Project Deliverable | 2016-10-10
Scope Statement:
|  | Start Date | 2016-08-27
|  | End Date | 2016-10-10
|  | Overall Progress | 50%
Tasks |  |  | Responsible | Start | End | Days | Status
Set kick-off meeting |  |  | Nguyễn Đỗ Quốc Tuấn | 2016-08-27 | 2016-08-28 | 1 | Completed
Agree on objectives |  |  | Ngô Thị Tường Vy | 2016-08-27 | 2016-08-28 | 1 | Completed
Detailed Reqs. | Layout |  | Nguyễn Đỗ Quốc Tuấn | 2016-08-28 | 2016-08-31 | 3 | Completed
Sizemap
Technical Reqs. | Hoạt động của nhà quản trị |  | Ngô Thị Tường Vy | 2016-08-28 | 2016-08-31 | 3 | Completed
Hoạt động của khách hàng
Database Development | Xác định thực thể, thuộc tính |  | Nguyễn Đỗ Quốc Tuấn | 2016-08-29 | 2016-09-02 | 4 | Completed
Xác định ràng buộc
Tạo cơ sở dữ liệu
Insert/Update/Query | Nhập dữ liệu bảng |  | Ngô Thị Tường Vy | 2016-09-02 | 2016-09-06 | 4 | Completed
UI Client | Giao diện website |  | Nguyễn Đỗ Quốc Tuấn | 2016-09-06 | 2016-09-08 | 2 | Completed
| Giao diện các trang nội dung website | Trang chủ | Nguyễn Đỗ Quốc Tuấn | 2016-09-08 | 2016-09-10 | 2 | Completed
|  | Giới thiệu | Ngô Thị Tường Vy | 2016-09-10 | 2016-09-12 | 2 | Completed
|  | Liên hệ | Ngô Thị Tường Vy | 2016-09-12 | 2016-09-14 | 2 | Completed
|  | Địa chỉ | Ngô Thị Tường Vy | 2016-09-14 | 2016-09-16 | 2 | Completed
|  | Đăng nhập | Nguyễn Đỗ Quốc Tuấn | 2016-09-10 | 2016-09-12 | 2 | Completed
|  | Đăng ký | Nguyễn Đỗ Quốc Tuấn | 2016-09-12 | 2016-09-14 | 2 | Completed
|  | Quần áo nam:Áo sơ mi, Áo thun, Áo khoác, Quần jean, Quần kaki, Quần tây, Quần lửng | Nguyễn Đỗ Quốc Tuấn | 2016-09-14 | 2016-09-24 | 10 | Completed
|  | Quần áo nữ:Áo sơ mi, Áo thun, Áo khoác, Áo đầm, Quần jean, Quần tây, Quần lửng, Váy | Ngô Thị Tường Vy | 2016-09-16 | 2016-09-24 | 8 | Completed
Connect Database |  |  | Nguyễn Đỗ Quốc Tuấn | 2016-09-24 | 2016-10-01 | 7 | Not started
API Development |  |  | Ngô Thị Tường Vy | 2016-09-24 | 2016-10-01 | 7 | Not started
Function 1 Tìm kiếm sản phẩm |  |  | Nguyễn Đỗ Quốc Tuấn | 2016-10-01 | 2016-10-05 | 4 | Not started
Function 2 Giỏ hàng |  |  | Nguyễn Đỗ Quốc Tuấn | 2016-10-05 | 2016-10-09 | 4 | Not started
Function 3 Đăng nhập |  |  | Ngô Thị Tường Vy | 2016-10-01 | 2016-10-05 | 4 | Not started
Function 4 Đăng ký |  |  | Ngô Thị Tường Vy | 2016-10-05 | 2016-10-09 | 4 | Not started
Testing |  |  | Nguyễn Đỗ Quốc Tuấn + Ngô Thị Tường Vy | 2016-10-09 | 2016-10-10 | 1 | Not started
Launch |  |  |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Lê Khánh | Team leader, Developer | 1. Make the plan of the project. 2. Assign task for your member. 3. Design GUI/database. 4. Code. 5. Write document | kanelorange@gmail.com
Trần Minh Trung | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test 4. Analysis & design the system. | minhtrungdhth10e@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team